Paper 7-4

DENTAL PROGRAMME BOARD

DENTAL PROJECT WORKSTREAMS UPDATE

SUPPLY WORKSTREAM

- Programme portfolio agreed and project scope has been completed

- WRT has provided a briefing paper on  modelling

- SpR has been appointed to the project.

- Checkpoint meeting held on 13 January.

- Funding approved for commissioning modelling work and potential tenderers identified.

- Developing a questionnaire to do a sample survey on gender mix.

DEMAND WORKSTREAM

- Finalised project scope, strategy and delivery approach

- SpR has been appointed to work on the data sources and update the 2004 workforce report as a starting point.

- Checkpoint meeting on 19 January to look at the data that has been collected

- Looking at updating the 1999 Heathrow exercise with a consensus conference on time spent on dental procedures.

- Continue further work on data collection and modelling

SKILL MIX WORKSTREAM

- The group’s second meeting on 10 December 2009 saw agreement on the evidence gathering process and confirmed the need for a consultation.

- The range of evidence for this workstream is broad and it is agreed that a significant effort should be made to capture as wide a range of views as possible.  Key to this is the engagement of DGPs/DCPs to gather best practices exemplars and to assess knowledge gaps on the competencies, legalities of the employment and remuneration of DCPs in extended clinical roles.

- A questionnaire has been drafted, which will be advertised online and in the dental press in 2010, with the aim of capturing as much evidence as possible.

- It is clear that, whilst there is an opportunity for an improved use of Skill Mix, there is a body of work to be done to understand the existing barriers to developing the roles of DCPs to maximise Skill Mix.

Next Steps

- Undertake visits

- Develop and launch online survey

- Analyse survey responses

- Report drafting

ORAL SURGERY WORKSTREAM

- Group has met for three meetings: initial scoping meeting in September 2009, oral evidence day in December 2009 and planning meeting in January 2010.

- Public consultation closed on 23 December 2009 with over 200 responses received.

- Group members agreed to undertake three visits at January 2010 meeting – Belfast, Guildford and South Wales.

- Drafting will continue with aim to present draft report in April 2010.

- Visits will feed into final report as case studies.

- RN to plan visits; write draft report; when visits completed, work with attendees and units to develop case studies.

SMALL SPECIALTIES WORKSTREAM

- First project meeting has taken place to

  - review the POD

  - review information sources

  - agree a work programme

  - Next Steps

    - find out any information/models on workforce planning in Restorative dentistry (Edinburgh/Sheffield model)

    - find out any if there is any information on Paediatric dentistry

    - find out about any information that can be provided from the GDC database

    - consult FDS about information the SACs hold on specialists and trainees .

- Next project meeting is on 22 February 2010.

FOUNDATION TRAINING WORKSTREAM

- Published curriculum for DF training

- Ministerial agreement in principle to the phasing in of DFT, timing and pace of implementation to be determined by further investigation of the costs and practicalities.

- Funded pilots of DFT commenced

- Initial estimates of numbers of service and training posts required for 2 year DFT for all new graduates.

- Launch of Learning Portfolio and Assessment Framework.

- Timeline to be developed for phased implementation within fiscal constraints upon NHS growth.

- Terminology to be changed in regulations, SFE, NHS workforce census etc to substitute DF1 for VDP and DF2 for SHO.